# SynapseOS Engineering Manual

Volume I – Governance
GOV-009 – Risk Management
Version 0.1.0 (Draft)

# Document Control

| Field | Value |
| --- | --- |
| Document ID | GOV-009 |
| Title | Risk Management |
| Version | 0.1.0 |
| Status | Draft |
| Author | Denver Jacobs |
| Created | 2026-07-09 |
| Last Updated | 2026-07-09 |
| Classification | Public |
| Related Documents | GOV-003, GOV-004, GOV-005, GOV-006, GOV-008 |

# 1. Purpose

Define a consistent framework for identifying, assessing, treating, monitoring and communicating risks that could affect SynapseOS.

# 2. Risk Management Objectives

Protect project continuity; reduce avoidable technical failure; identify security and operational threats early; preserve architectural adaptability; support evidence-based decisions; and maintain explicit ownership of material risks.

# 3. Scope

This standard applies to strategic, product, technical, architectural, security, privacy, legal, licensing, operational, financial, dependency, supply-chain, AI-model, data, deployment, continuity and reputational risks.

# 4. Risk Principles

• Risks are recorded rather than kept only in conversation.
• Material risks have an owner.
• Treatment effort is proportional to exposure.
• High-impact irreversible decisions receive greater scrutiny.
• Residual risk is explicitly accepted, transferred, reduced or avoided.
• Risks are reviewed throughout the system lifecycle.

# 5. Risk Lifecycle

1. Identify the risk.
2. Describe cause, event and consequence.
3. Assign category and owner.
4. Assess likelihood and impact.
5. Determine inherent exposure.
6. Select treatment.
7. Implement controls.
8. Assess residual exposure.
9. Monitor indicators.
10. Close or escalate.

# 6. Likelihood Scale

1 – Rare: Exceptional circumstances only.
2 – Unlikely: Possible but not expected.
3 – Possible: Could occur.
4 – Likely: Expected in many circumstances.
5 – Almost Certain: Expected frequently or imminently.

# 7. Impact Scale

1 – Insignificant: Minimal disruption and negligible recovery effort.
2 – Minor: Limited degradation with straightforward recovery.
3 – Moderate: Material disruption, rework or delayed milestones.
4 – Major: Serious security, operational, financial or architectural harm.
5 – Critical: Threatens project continuity, trust, legal position or core platform viability.

# 8. Risk Scoring

Risk Score = Likelihood × Impact. Scores guide prioritisation but do not replace judgement. A low-likelihood catastrophic risk may still require executive attention.

# 9. Risk Rating Bands

1–4 Low: Monitor through routine controls.
5–9 Moderate: Assign treatment and review.
10–16 High: Prioritised mitigation and frequent review.
17–25 Critical: Immediate escalation; implementation or release may be blocked.

# 10. Treatment Options

Avoid – Stop or redesign the activity.
Reduce – Introduce controls that lower likelihood or impact.
Transfer – Shift defined exposure through contracts, insurance or managed services where appropriate.
Accept – Explicitly retain residual risk with documented rationale.

# 11. Mandatory Risk Categories

Strategic; Architecture; Security; Privacy; AI Provider; Model Behaviour; Data; Dependency and Supply Chain; Availability; Performance; Financial Sustainability; Legal and Licensing; Skills and Key-Person Dependency; Documentation Drift; Deployment; Reputation.

# 12. AI-Specific Risks

SynapseOS must explicitly consider hallucination, prompt injection, unsafe tool execution, model drift, provider outages, provider policy changes, uncontrolled autonomy, hidden model dependencies, data leakage, non-determinism, excessive cost and misleading confidence.

# 13. Architectural Obsolescence Risk

Because AI evolves rapidly, SynapseOS shall reduce obsolescence risk through provider abstraction, replaceable modules, open interfaces, incremental releases, limited irreversible commitments and regular architecture reviews.

# 14. Security Risk Escalation

Suspected credential exposure, unauthorised access, arbitrary code execution, supply-chain compromise, destructive autonomous action or material data leakage must be treated as urgent and may block releases.

# 15. Risk Register Requirements

Each material risk record should contain: Risk ID; title; description; category; cause; consequence; owner; likelihood; impact; inherent score; controls; treatment actions; target date; residual score; status; indicators; review date; related ARCH/RFC/ADR references.

# 16. Risk Ownership

Risk owners are accountable for monitoring and treatment coordination. Ownership does not imply that one person must perform every mitigation task.

# 17. Review Cadence

Critical risks: continuous attention and at least weekly formal review while active.
High risks: at least monthly.
Moderate risks: at least quarterly.
Low risks: at least semi-annually or when conditions change.

# 18. Release Risk

Before a stable release, unresolved high and critical risks must be reviewed explicitly. Acceptance of material residual risk requires recorded approval.

# 19. Risk Communication

Risk reporting shall be concise, factual and decision-oriented. Reports should identify exposure, trend, overdue treatments, blockers and decisions required.

# 20. Initial Strategic Risks

RISK-001 Rapid AI evolution makes architecture obsolete.
RISK-002 Excessive documentation delays working software.
RISK-003 Dependence on a single AI provider.
RISK-004 AI-generated code introduces hidden defects.
RISK-005 Founder/key-person dependency.
RISK-006 Scope expansion prevents delivery.
RISK-007 Security controls lag behind autonomous capabilities.
RISK-008 Third-party dependency or supply-chain compromise.
RISK-009 Project costs exceed sustainable funding.
RISK-010 Documentation diverges from implementation.

# 21. Success Criteria

Risk management is successful when material threats are visible early, owned, treated proportionally, linked to decisions and reviewed before they become incidents.

# 22. Open Questions

• What risk appetite should apply to experimental AI autonomy?
• Which risks require founder approval for acceptance?
• When should independent security review become mandatory?
• Which risk indicators should be automated in SynapseOS itself?

# Appendix A – Risk Register Template

| Risk ID | Risk | Owner | Likelihood | Impact | Score | Treatment | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RISK-001 | Architecture obsolescence | TBD | 3 | 5 | 15 | Reduce | Open |
| RISK-002 | Documentation delays delivery | TBD | 4 | 4 | 16 | Reduce | Open |
| RISK-003 | Single-provider dependency | TBD | 3 | 4 | 12 | Reduce | Open |

# Revision History

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| 0.1.0 | 2026-07-09 | Denver Jacobs | Initial draft |

# Approval

Author: Denver Jacobs ____________________  Date: __________

Architecture Review: ____________________  Date: __________

Approved By: ___________________________  Date: __________